## Risk_Register_Detailed
Risk ID | Risk Category | Risk Description | Inherent Risk | Control Effectiveness | Residual Risk | Remediation Owner | Status | Regulatory Mapping | Last Updated | Likelihood (1-5) | Impact (1-5) | Control Gap | Remediation Target Date | Evidence of Progress
R‑001 | Cloud Misconfiguration | Misconfigured S3 bucket (public read) could expose UK customer PII (names, addresses, transaction history). | High | Partially Effective – AWS S3 block public access enabled at org level, but per-bucket overrides possible. | High | Cloud Engineering | In Progress | NIST CSF PR.IP‑1, UK DPA Art.32 | 02‑Apr‑2026 | 4 | 5 | No automated CSPM; bucket-level audit disabled | 2026-06-30 | CSPM PoC started with AWS Config
R‑002 | Identity & Access Mgmt | Over‑privileged IAM roles: 15 DevOps engineers have admin access to production AWS account. | High | Ineffective – No automated least-privilege; manual reviews only once per quarter. | High | IAM Team | In Progress | ISO 27001 A.9.2, PCI DSS 7.1 | 02‑Apr‑2026 | 5 | 4 | No CI/CD for IAM policy generation | 2026-07-15 | IAM roles inventoried; starting access analysis
R‑003 | Data Residency | Replication pipeline may temporarily store UK customer data in AWS eu‑west‑1 (Ireland) despite UK region requirement. | Medium | Partially Effective – Data classification incomplete; legal review ongoing. | Medium | Data Governance | In Progress | UK DPA / GDPR (Art. 44‑49) | 02‑Apr‑2026 | 3 | 4 | No automated data flow mapping tool | 2026-08-30 | Data map drafted for 5 core services
R‑004 | Vendor Lock‑in | Heavy use of AWS Lambda, DynamoDB, and Step Functions could make migration to another cloud costly and slow. | Low | Effective – Multi‑cloud strategy documented; containerisation of stateless services underway. | Low | Architecture | Mitigated | N/A (business risk) | 02‑Apr‑2026 | 2 | 2 | None – architecture already decoupling | 2026-05-15 | 40% of services containerised
R‑005 | Insecure APIs | New payment initiation API (REST) not fully scanned for OWASP Top 10 vulnerabilities (e.g., injection, broken auth). | High | Partially Effective – SAST in CI/CD, but DAST not integrated; manual pen tests quarterly. | High | Product Security | In Progress | PCI DSS 6.5, NIST CSF PR.IP‑1 | 02‑Apr‑2026 | 4 | 5 | DAST pipeline missing; no rate limiting | 2026-05-31 | DAST tool selected (OWASP ZAP)
R‑006 | Lack of Visibility | Cloud logs (CloudTrail, VPC Flow Logs) not fully ingested into central SIEM (Splunk). | Medium | Partially Effective – Logging enabled but only for 7 days; no real-time alerting. | Medium | SecOps | In Progress | NIST CSF DE.AE‑3, PCI DSS 10.2 | 02‑Apr‑2026 | 3 | 3 | SIEM ingestion licence exhausted | 2026-06-30 | Increased log retention to 30 days
R‑007 | Insider Threat | Privileged access to AWS console not continuously monitored; no UEBA for anomalous behaviour. | Medium | Partially Effective – Session recording enabled for 5 critical roles; no automated anomaly detection. | Medium | IAM Team | Not Started | NIST CSF PR.AC‑5 | 02‑Apr‑2026 | 3 | 4 | No UEBA tool; access reviews annual only | 2026-09-30 | Initial user behaviour baseline defined
R‑008 | Backup & Recovery | Automated backups for DynamoDB enabled but not tested for restore within RPO (15 min) / RTO (4 hours). | High | Ineffective – Backups exist but restore test never performed. | High | Cloud Engineering | In Progress | NIST CSF RC.RP‑1, FCA SYSC 15A | 02‑Apr‑2026 | 4 | 4 | No restore testing automation | 2026-06-15 | First restore test scheduled 20‑Jun
R‑009 | Cryptography & Key Mgmt | Encryption keys for RDS databases stored in AWS KMS, but key rotation policy is manual (90 days). | Low | Effective – KMS automatic rotation enabled (every 365 days) but not aligned to internal 90‑day policy. | Low | Security Architecture | Not Started | PCI DSS 3.6, NIST CSF PR.DS‑2 | 02‑Apr‑2026 | 2 | 3 | Internal policy out of sync with KMS capability | 2026-07-31 | Draft policy update under review
R‑010 | Supply Chain / Third‑Party | Cloud provider’s UK region may be affected by upstream SaaS dependencies (e.g., monitoring vendor, CDN). | Medium | Partially Effective – Supplier security reviews done annually; no real‑time dependency monitoring. | Medium | Third‑Party Risk | In Progress | NIST CSF ID.SC‑2, EBA Guidelines | 02‑Apr‑2026 | 3 | 3 | No dependency monitoring tool | 2026-08-31 | Mapped top 10 critical dependencies

## Summary
Total High Residual Risks | 4
Row Labels | Count of Risk ID
Architecture | 1
Cloud Engineering | 2
Data Governance | 1
IAM Team | 2
Product Security | 1
SecOps | 1
Security Architecture | 1
Third‑Party Risk | 1
Grand Total | 10