## IBS_Tracker
Service ID | IBS Name | Description | Impact Tolerance (mins) | Current RAG | Last Incident Date | Incident Duration (mins) | Issue Description | Root Cause | Remediation Action | Remediation Owner | Remediation Due Date | Status
BS‑001 | Instant P2P Transfers | Real‑time money transfer between UK personal accounts | 120 | Amber | 2026-03-15 | 35 | API latency >5 sec for 30% of requests | DB connection pool exhausted | Increase pool size + circuit breaker | Platform Eng | 2026-04-30 | In Progress
IBS‑002 | Merchant Settlement | End‑of‑day settlement to merchant bank accounts | 240 | Green | 2026-03-10 | 180 | Batch job failed for two cycles | SFTP permission change | Retry mechanism + monitoring | Payments Eng | 2026-04-15 | Completed
IBS‑003 | Checkout Payment Processing | Card payment authorisation at online checkout | 30 | Red | 2026-03-28 | 65 | 15% decline rate – gateway timeout | TLS certificate expired | Auto certificate rotation + secondary acquirer | Payments Rel | 2026-04-20 | At Risk
IBS‑004 | Fraud Score API | Real‑time fraud risk scoring | 15 | Amber | 2026-03-20 | 22 | Latency >1 sec (SLO=200ms) | Memory leak in container | Fix leak + horizontal autoscaling | ML Ops | 2026-05-10 | Not Started
IBS‑005 | Customer Statements | Monthly downloadable PDF statements | 1440 (24h) | Green | 2026-02-05 | 480 | Reports delayed 8 hours | DB lock contention | Partition tables + read replica | Data Eng | 2026-05-15 | Completed

## Issue_Remediation_Log
Issue ID | IBS ID | Date Identified | Issue Summary | Severity | Root Cause Category | Remediation Task | Task Owner | Planned Date | Actual Completion | Status
IR‑001 | IBS‑001 | 15‑Mar‑2026 | API latency >5 sec | High | Capacity | Increase connection pool size | Platform Eng | 25‑Mar‑2026 | 22‑Mar‑2026 | Done
IR‑002 | IBS‑001 | 15‑Mar‑2026 | API latency >5 sec | High | Resilience | Implement circuit breaker | Platform Eng | 30‑Apr‑2026 | – | In Progress
IR‑003 | IBS‑003 | 28‑Mar‑2026 | 15% decline rate | Critical | Certificate Mgmt | Automate TLS rotation | Platform Sec | 20‑Apr‑2026 | – | At Risk
IR‑004 | IBS‑003 | 28‑Mar‑2026 | No failover | Critical | Architecture | Add secondary acquirer | Payments Rel | 15‑May‑2026 | – | Not Started
IR‑005 | IBS‑004 | 20‑Mar‑2026 | High latency | High | Memory leak | Fix memory leak | ML Ops | 05‑May‑2026 | – | In Progress

## Product_Change_Governance
Change ID | Product/Feature | Change Type | Security Assessment Status | DAST Result | SAST Result | Pen Test Result | Third‑Party Library Scan | Go‑Live Readiness | Planned Go‑Live Date | Security Approver | Notes
CH‑001 | New Checkout Flow | Major | In Review | Pass | Pass (warnings) | Pending | Pass | Amber | 2026-05-15 | CISO Office | Pen test scheduled 10‑May
CH‑002 | Mobile App v4.2 | Minor | Approved | Pass | Pass | Not required | Pass | Green | 2026-04-05 | AppSec Lead | Ready
CH‑003 | Cloud Migration Phase 1 | Infrastructure | Blocked | Fail (critical) | N/A | N/A | Pass | Red | 2026-04-20 | CISO | SQL injection found – fix required
CH‑004 | Fraud Rules Update | Patch | Approved | N/A | Pass | Not required | Pass | Green | 2026-04-01 | AppSec Lead | Deployed
CH‑005 | Real‑time Balance API | Major | In Review | Pass | Pass (2 highs fixed) | Pass | Pass (log4j ok) | Amber | 2026-05-30 | CISO Office | Awaiting pen test report
CH‑006 | Data Warehouse Migration | Major | Approved | Pass | Pass | Pass | Pass | Green | 2026-06-10 | Data Governance | All gates passed